## Execution_Tracker
Phase | Task ID | Task Name | Description | Owner | Start Date | End Date | Status | % Complete | Dependencies | Notes
Phase 1 | T001 | Requirement Gathering | Document business needs |  |  |  | Not Started | 0%
Phase 2 | T002 | Product Setup | Create and configure products |  |  |  | Not Started | 0% | T001
Phase 2 | T003 | Customer Setup | Create customers |  |  |  | Not Started | 0% | T001
Phase 2 | T004 | Vendor Setup | Create vendors |  |  |  | Not Started | 0% | T001
Phase 3 | T005 | Procurement Flow | PO to Invoice |  |  |  | Not Started | 0% | T002,T004
Phase 3 | T006 | Sales Flow | SO to Invoice |  |  |  | Not Started | 0% | T002,T003
Phase 3 | T007 | Inventory Setup | Warehouses and stock |  |  |  | Not Started | 0% | T002
Phase 4 | T008 | Integration Setup | Data import setup |  |  |  | Not Started | 0% | T005
Phase 5 | T009 | Custom Development | Build table/form/entity |  |  |  | Not Started | 0% | T008
Phase 6 | T010 | Security Setup | Roles and access |  |  |  | Not Started | 0% | T001
Phase 7 | T011 | Reporting | Create reports |  |  |  | Not Started | 0% | T005,T006
Phase 8 | T012 | Testing | Execute UAT |  |  |  | Not Started | 0% | T005-T011